## Base data
Milestone | Iteration | Est. Time Allotted (days) | Actual Time Spent (days) | Status | User Story | Owner | Task
1 | 1 | 2 |  |  | Any user should be able to search by location and property features only | Kieu | Create and publish webpage UI Design requirements.
1 | 1 | 0.5 |  |  | Any user should be able to search by location and property features only | Alex | Create and publish UI design of static placeholder webpages.
1 | 1 | 2 |  |  | Any user should be able to search by location and property features only | Rutuja | Source data for use in development.
1 | 1 | 2 |  |  | Any user should be able to search by location and property features only | Sam/Phillip | Test and run simple queries in Django. Develop back-end code for functional static placeholder webpages.
1 | 1 | 6 |  |  | Any user should be able to search by location and property features only | Rutuja | Look into database structure to house source dat
1 | 2 | 4 |  |  | Any user would be able to input their preference parameters when they open the web app as an added feature | Kieu | Create and publish webpage UI Design and search parameters requirements.
1 | 2 | 0.5 |  |  | Any user would be able to input their preference parameters when they open the web app as an added feature | Alex | Create and publish UI design of webpages from iteration requirements.
1 | 2 | 2 |  |  | Any user would be able to input their preference parameters when they open the web app as an added feature | Rutuja | Source data for use in development as needed.
1 | 2 | 2 |  |  | Any user would be able to input their preference parameters when they open the web app as an added feature | Rutuja | Build database structure and have data for use.
1 | 2 | 6 |  |  | Any user would be able to input their preference parameters when they open the web app as an added feature | Sam/Phillip | Develop back-end code for webpages identified for iteration 2.
1.5 | 3 | 3 |  |  | A registered user is able to save listings, contact housing hosts and access other web features on the web pages | Alex | Create and publish UI design of associated webpages.
1.5 | 3 | 0.5 |  |  | A registered user is able to save listings, contact housing hosts and access other web features on the web pages | Kieu | Create and publish webpage UI Design requirements as needed.
1.5 | 3 | 2 |  |  | A registered user is able to save listings, contact housing hosts and access other web features on the web pages | Rutuja | Build database structure and have data for use.
1.5 | 3 | 5 |  |  | A registered user is able to save listings, contact housing hosts and access other web features on the web pages | Sam/Phillip | Test and run simple queries in Django.
1.5 | 3 | 6 |  |  | A registered user is able to save listings, contact housing hosts and access other web features on the web pages | Sam/Phillip | Develop back-end code for associated webpages and test codes.
2 | 4 | 0.5 |  |  | A user can make a change to their preferences without starting over | Kieu | Create and publish webpage UI Design requirements as needed
2 | 4 | 2 |  |  | Any user should be able to search by location and property features only | Alex | Create and publish UI design of associated webpages.
2 | 4 | 1 |  |  | A user can make a change to their preferences without starting over | Rutuja | Maintain and address any database issues.
2 | 4 | 6 |  |  | A user can make a change to their preferences without starting over | Sam/Phillip | Develop back-end code for associated webpage. Test codes.
2 | 5 | 0.5 |  |  | A user can see both a map view and text listings of search results | Kieu | Create and publish webpage UI Design requirements as needed
1 | 1 | 2 |  |  | Any user should be able to search by location and property features only | Alex | Create and publish UI design of associated webpages.
2 | 5 | 1 |  |  | A user can see both a map view and text listings of search results | Rutuja | Maintain and address any database issues.
2 | 5 | 6 |  |  | A user can see both a map view and text listings of search results | Sam/Phillip | Develop back-end code for associated webpage. Test codes.
2 | 6 | 6 |  |  | A user should be able to sort the listings based on their personalized rankings preference | Sam/Phillip | Develop back-end code for associated webpage. Test codes.
2 | 6 | 2 |  |  | A user should be able to sort the listings based on their personalized rankings preference | Team | Conduct sample user testing among team members.

## Chart
| Owner | Alex | Kieu | Rutuja | Rutuja/Kieu | Sam/Phillip | Alex | Kieu | Rutuja | Rutuja | Sam/Phillip | Alex | Kieu | Rutuja | Sam/Phillip | Sam/Phillip | Kieu | Alex | Rutuja | Sam/Phillip | Kieu | Alex | Rutuja | Sam/Phillip | Sam/Phillip | Team
| Task | Create and publish UI design of static placeholder webpages. | Create and publish webpage UI Design requirements. | Source data for use in development. | Look into database structure to house source dat | Test and run simple queries in Django. Develop back-end code for functional static placeholder webpages. | Create and publish UI design of webpages from iteration requirements. | Create and publish webpage UI Design and search parameters requirements. | Source data for use in development as needed. | Build database structure and have data for use. | Develop back-end code for webpages identified for iteration 2. | Create and publish UI design of associated webpages. | Create and publish webpage UI Design requirements as needed. | Build database structure and have data for use. | Test and run simple queries in Django. | Develop back-end code for associated webpages and test codes. | Create and publish webpage UI Design requirements as needed | Create and publish UI design of associated webpages. | Maintain and address any database issues. | Develop back-end code for associated webpage. Test codes. | Create and publish webpage UI Design requirements as needed | Create and publish UI design of associated webpages. | Maintain and address any database issues. | Develop back-end code for associated webpage. Test codes. | Develop back-end code for associated webpage. Test codes. | Conduct sample user testing among team members.
| Milestone | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 2
| Iteration | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 6
| Est. Time Allotted (days) | 1 | 1 | 1 | 1 | 4 | 1 | 0.5 | 1 | 1 | 4 | 1 | 0.5 | 2 | 5 | 5 | 0.5 | 1 | 1 | 5 | 0.5 | 1 | 1 | 4 | 5 | 2 | 50
| Actual Time Spent (days) | 1 | 0.35 | 0.25 | 0.1 | 2.5
| Start | Iteration 1 | Iteration 2 | iteration 3 | Iteration 4 | Iteration 5 | Iteration 6
Estimated Time (days) | 50 | 42 | 34.5 | 21 | 13.5 | 7 | 0
Actual Time (days) | 50 | 45.8