## Base data
Owner | Milestone | Iteration | Due Dates | Course Milestones | Est. Time Allotted (days) | Actual Time Spent (days) | User Story | Task
Alex | 1 | 1 | 2019-10-01 | Part B - 10/08 | 1 | 1 | Any user should be able to search by location and property features only | Create and publish UI design for Iteration 1 webpages.
Kieu | 1 | 1 | 2019-10-01 | Part B - 10/08 | 0.25 | 0.35 | Any user should be able to search by location and property features only | Create and publish webpage UI Design requirements for Iteration 1 webpages.
Rutuja | 1 | 1 | 2019-10-01 | Part B - 10/08 | 1 | 0.25 | Any user should be able to search by location and property features only | Look into database structure to house source data
Sam/Phillip | 1 | 1 | 2019-10-01 | Part B - 10/08 | 4 | 2.5 | Any user should be able to search by location and property features only | Test and run simple queries in Django. Develop back-end code for functional static placeholder webpages for Part B.
Rutuja | 1 | 1 | 2019-10-01 | Part B - 10/08 | 1 | 0.1 | Any user should be able to search by location and property features only | Source data for use in development.
Sam | 1 | 2 | 2019-10-15 | Part C - 11/06 | 1 |  | Any user would be able to input their preference parameters when they open the web app as an added feature | Build database structure.
Alex | 1 | 2 | 2019-10-15 | Part C - 11/06 | 1 |  | Any user would be able to input their preference parameters when they open the web app as an added feature | Create and publish UI design for iteration 2 webpages.
Kieu | 1 | 2 | 2019-10-15 | Part C - 11/06 | 0.25 |  | Any user would be able to input their preference parameters when they open the web app as an added feature | Create and publish webpage UI Design requirements for Iteration 2 webpages.
Sam/Phillip | 1 | 2 | 2019-10-15 | Part C - 11/06 | 4 |  | Any user would be able to input their preference parameters when they open the web app as an added feature | Develop back-end code for webpages identified for iteration 2 requirements.
Rutuja | 1 | 2 | 2019-10-15 | Part C - 11/06 | 1 |  | Any user would be able to input their preference parameters when they open the web app as an added feature | Source data for use in development as needed.
Alex | 1.5 | 3 | 2019-10-29 | Part C - 11/06 | 0.5 |  | A registered user is able to save listings, contact housing hosts and access other web features on the web pages | Create and publish UI designs for Iteration 1.5 webpages
Kieu | 1.5 | 3 | 2019-10-29 | Part C - 11/06 | 0.25 |  | A registered user is able to save listings, contact housing hosts and access other web features on the web pages | Create and publish data logic and analytics requirements per preference. How the data should be analyzed and used in search results.
Kieu | 1.5 | 3 | 2019-10-29 | Part C - 11/06 | 0.25 |  | A registered user is able to save listings, contact housing hosts and access other web features on the web pages | Create and publish data source requirements in regards to required fields and values per preference parameter.
Kieu | 1.5 | 3 | 2019-10-29 | Part C - 11/06 | 0.25 |  | A registered user is able to save listings, contact housing hosts and access other web features on the web pages | Create and publish webpage UI Design requirements for Iteration 3 webpages.
Phillip | 1.5 | 3 | 2019-10-29 | Part C - 11/06 | 1 |  | A registered user is able to save listings, contact housing hosts and access other web features on the web pages | Test code for Iteration 3 requirements.
Sam | 1.5 | 3 | 2019-10-29 | Part C - 11/06 | 1 |  | A registered user is able to save listings, contact housing hosts and access other web features on the web pages | Test code for Iteration 3 requirements.
Sam/Phillip | 1.5 | 3 | 2019-10-29 | Part C - 11/06 | 5 |  | A registered user is able to save listings, contact housing hosts and access other web features on the web pages | Develop back-end code for webpages identified for iteration 3 requirements.
Rutuja | 2 | 4 | 2019-11-12 | Part D - 12/11 | 0.5 |  | A user can make a change to their preferences without starting over. | Maintain and address any database issues Iteration 4 requirements.
Alex | 2 | 4 | 2019-11-12 | Part D - 12/11 | 1 |  | A user can make a change to their preferences without starting over. | Create and publish UI designs for Iteration 4 webpages
Kieu | 2 | 4 | 2019-11-12 | Part D - 12/11 | 0.25 |  | A user can make a change to their preferences without starting over. | Create and publish webpage UI Design requirements for Iteration 4 webpages.
Sam/Phillip | 2 | 4 | 2019-11-12 | Part D - 12/11 | 5 |  | A user can make a change to their preferences without starting over. | Develop back-end code for associated webpage for iteration 4 requirements.
Sam | 2 | 4 | 2019-11-12 | Part D - 12/11 | 1 |  | A user can make a change to their preferences without starting over. | Maintain and address any database issues Iteration 4 requirements.
Alex | 2 | 4 | 2019-11-12 | Part D - 12/11 | 1 |  | A user can make a change to their preferences without starting over. | Test code and provide feedback for Iteration 4 requirements.
Rutuja | 2 | 4 | 2019-11-12 | Part D - 12/11 | 1 |  | A user can make a change to their preferences without starting over. | Test code and provide feedback for Iteration 4 requirements.
Rutuja | 2 | 5 | 2019-11-26 | Part D - 12/11 | 0.5 |  | A user can see both a map view and text listings of search results. | Maintain and address any database issues Iteration 5 requirements.
Alex | 2 | 5 | 2019-11-26 | Part D - 12/11 | 0.5 |  | A user can see both a map view and text listings of search results. | Create and publish UI designs for Iteration 5 webpages
Kieu | 2 | 5 | 2019-11-26 | Part D - 12/11 | 0.25 |  | A user can see both a map view and text listings of search results. | Create and publish webpage UI Design requirements for Iteration 5 webpages.
Sam/Phillip | 2 | 5 | 2019-11-26 | Part D - 12/11 | 5 |  | A user can see both a map view and text listings of search results. | Develop back-end code for associated webpage for iteration 5 requirements.
Sam | 2 | 5 | 2019-11-26 | Part D - 12/11 | 0.5 |  | A user can see both a map view and text listings of search results. | Maintain and address any database issues Iteration 5 requirements.
Alex | 2 | 5 | 2019-11-26 | Part D - 12/11 | 1 |  | A user can see both a map view and text listings of search results. | Test code and provide feedback for Iteration 5 requirements.
Rutuja | 2 | 5 | 2019-11-26 | Part D - 12/11 | 1 |  | A user can see both a map view and text listings of search results. | Test code and provide feedback for Iteration 5 requirements.
Rutuja | 2 | 6 | 2019-12-10 | Part D - 12/11 | 0.5 |  | A user should be able to sort the listings based on their personalized rankings preference | Maintain and address any database issues Iteration 6 requirements.
Alex | 2 | 6 | 2019-12-10 | Part D - 12/11 | 0.5 |  | A user should be able to sort the listings based on their personalized rankings preference | Create and publish UI designs for Iteration 6 webpages
Kieu | 2 | 6 | 2019-12-10 | Part D - 12/11 | 0.25 |  | A user should be able to sort the listings based on their personalized rankings preference | Create and publish webpage UI Design requirements for Iteration 6 webpages.
Sam | 2 | 6 | 2019-12-10 | Part D - 12/11 | 0.5 |  | A user should be able to sort the listings based on their personalized rankings preference | Maintain and address any database issues Iteration 6 requirements.
Alex | 2 | 6 | 2019-12-10 | Part D - 12/11 | 1 |  | A user should be able to sort the listings based on their personalized rankings preference | Test code and provide feedback for Iteration 6 requirements.
Kieu | 2 | 6 | 2019-12-10 | Part D - 12/11 | 0.25 |  | A user should be able to sort the listings based on their personalized rankings preference | Test code and provide feedback for Iteration 6 requirements.
Rutuja | 2 | 6 | 2019-12-10 | Part D - 12/11 | 1 |  | A user should be able to sort the listings based on their personalized rankings preference | Test code and provide feedback for Iteration 6 requirements.
Sam/Phillip | 2 | 6 | 2019-12-10 | Part D - 12/11 | 5 |  | A user should be able to sort the listings based on their personalized rankings preference | Develop back-end code for associated webpage for iteration 6 requirements.
50.25

## Burndown Chart
ALLOCATED VS SPENT
| Start | Iteration 1 | Iteration 2 | iteration 3 | Iteration 4 | Iteration 5 | Iteration 6
Estimated Time (days) | 50.25 | 7.25 | 7.25 | 8.25 | 9.75 | 8.75 | 9
Actual Time (days) | 50.25 | 4.2 | 0 | 0 | 0 | 0 | 0
Burndown
| Start | Iteration 1 | Iteration 2 | iteration 3 | Iteration 4 | Iteration 5 | Iteration 6
Estimated Time (days) | 50.25 | 43 | 35.75 | 27.5 | 17.75 | 9 | 0
Actual Time (days) | 50.25 | 46.05 | 46.05

## User Story Reference
ITERATION | USER STORY
1 | Any user should be able to search by location and property features only
2 | Any user would be able to input their preference parameters when they open the web app as an added feature
3 | A registered user is able to save listings, contact housing hosts and access other web features on the web pages
4 | A user can make a change to their preferences without starting over
5 | A user can see both a map view and text listings of search results
6 | A user should be able to sort the listings based on their personalized rankings preference